## Sheet1
DEFECT REPORT - STATE TRANSITION
Defect Id | Module Name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type/ Test Cycle | Test Case No. | Defect Count | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachments | Comments
DF_001 | FlighT | The Flight tab is found to be unable to navigate user to Flight page. | Detailed Description: In Home page it is found that the user is unable to navigate to "Flight" page by clicking on "Flight" tab. Steps To reproduce the bug: 1. Open Browser . 2. Enter URL for the website. 3. Click on "Flight" tab. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the user is unable to navigate to Flight page as expected. | Coding | Internet Explorer | Internal Dev | P2 | Medium | 1.3.1 | 1 | 27/11/2018 | Nilesh Kalwar | Rutuja Kulkarni | ACT |  | TC_002
DF_002 | Register | The "Register " tab is found to be unable to navigate user to Register page. | Detailed Description: In Home page it is found that the user is unable to navigate to "Register" page by clicking on "Register" tab. Steps To reproduce the bug: 1. Open Browser . 2. Enter URL for the website. 3. Click on "Register" tab. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the user is unable to navigate to Register page as expected. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 1 | 27/11/2018 | Nilesh Kalwar | Rutuja Kulkarni | ACT |  | TC_003
DF_003 | SignOn | The "Sign On" tab is found to be unable to navigate user to Register page. | Detailed Description: In Home page it is found that the user is unable to navigate to "Register" page by clicking on "Register" tab. Steps To reproduce the bug: 1. Open Browser . 2. Enter URL for the website. 3. Click on "Register" tab. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the user is unable to navigate to Register page as expected. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 1 | 27/11/2018 | Nilesh Kalwar | Rutuja Kulkarni | ACT |  | TC_004
DF_004 | Cruise_Special | The "Cruise Special" tab is found to be unable to navigate user to "Cruise Special" page. | Detailed Description: In Home page it is found that the user is unable to navigate to "Register" page by clicking on "Register" tab. Steps To reproduce the bug: 1. Open Browser . 2. Enter URL for the website. 3. Click on "Register" tab. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the user is unable to navigate to Register page as expected. | Coding | Internet Explorer | Internal Dev | P3 | Low | 1.3.1 | 1 | 27/11/2018 | Nilesh Kalwar | Rutuja Kulkarni | ACT |  | TC_007